## Assumptions
Story Creation
Assumption:- | 1. Followed Fibonacci Series to assign Story Points (0,1,1,2,3,5,8,13,….)
2. Considering 1 Point = 1 person a Day ( 8-hours)
3. We can overlap story if required.
4. We can work a bit more on one of the weekends ( optional)
5. Considering only 1 developer as of now
6. We can involve Fresher from 2nd or 3rd Sprint onwards and till that time S/he can be trained.
7. Developers will create Task as per Story
Sprint Planning
|  | Sprint | Duration | Time-Line
|  | SP1 | 3 week | 28 Nov - 18 Dec
|  | SP2 | 3 week | 19 Dec - 8 Jan
|  | SP3 | 3 week | 9 Jan - 29 Jan
|  | SP4 | 3 week | 30 Jan - 19 Feb
|  | SP5 | 3 week | 20 Feb - 12 Mar
|  | SP6 | 3 week | 13 Mar - 2 Apr
|  | SP7 | 3 week | 3 Apr - 23 Apr
|  | SP8 | 3 week | 24 Apr - 14 May
|  | SP9 | 3 week | 15 May - 4 Jun
|  | GA | 3 week | 5 Jun - 25 Jun

## Product_Backlog
Tentative Date for Release of Product -25June 2025
Product Backlogs | [5 empty] | Duration
Phase 1 :- Working for technical Query Resolution
Epic 1 : - Development of Web Page to be accessed by Users
Features to be included:-
1 | Web Page Creation | Web page will have different page link such as User Login, User Profile, Expert Login and Expert Profile, Product profile with description (what is it and purpose) |  |  |  |  | SP2
2 | User Signup | [5 empty] | SP1
| I. New User:- | Registration with (Mobile No, Email)
| II. New password | Password Creation ( support Password Policy)
| III. User Confirmation | ( OTP via mail /Mobile no)
3 | User Profile Creation | [5 empty] | SP3
| Name | Address | Mobile No /Alternate No | Mail_ID
4 | Profile Management | [5 empty] | SP4
| I. Existing User | Login ID/User ID, Password
| II. Forget Password | OTP activation
III. Security Questions
IV. Modification of Customer details
5 | User Search /Technical Query | Problem Statement | Expert Search | Connection | Resolution / Help Initiated |  | SP5
6 | Payment mechanism to Trinade
Epic 2 : - Development of Web Page to be accessed by Expert
Features to be included:-
1 | Expert Signup |  |  |  |  | SP1
| I. New Expert:- | Registration with (Mobile No, Email)
| II. New password | Password Creation ( support Password Policy)
| III. Expert Confirmation | ( OTP via mail /Mobile no)
2 | Expert Profile Creation |  |  |  |  | SP3
| Name | Address | Mobile No /Alternate No | Mail_ID
3 | Profile Management |  |  |  |  | SP4
| I. Existing Expert | Login ID/Expert ID, Password
| II. Forget Password | OTP activation
III. Security Questions
IV. Modification of Customer details
4 | Technical Query | Problem Statement | User raised | Connection | Resolution / Help Initiated | SP5
5 | Payment mechanism to Expert from Trinade |  |  |  |  | SP7
Epic 3 : - Development of Linking and DB management by Trinade
Features to be included:-
1 | Communicator |  |  |  |  | SP6
| I. 2 way Communication | Chat Communication, Voice Communication, Video Communication
| II. Screen Sharing for Problem Solving | 2 way screen sharing feature, Control sharing
| III. Secure Communication | Security with data saving and connectivity
2 | Rating & Review |  |  |  |  | SP8
| I. Rating Facility by User | Rating on the basis of Resolution time and Solution provided, Mainly by Users, Once committed cannot be changed
| II. Review comments by User | Review comments on the basis of Resolution time and Solution provided, Mainly by Users, Once submitted cannot be be modified.
| III. Visibility to eavery one included Experts. | Acknowledgement by Expert.
3 | Database Management at Trinade End |  |  |  |  | SP9
| I. Storing all details | User profiles, Expert Profiles
| II. Maintaining History of Payments | Payment made by Users, Payment made to Experts, Commissions etc
| III. Maintain History of Resultion of problem | Queries & Resolutions history for particular duration at concent of Experts, Ratings and Comments

## Sprint_Backlogs
Sequential Order | Order of Execution | Features | Description | Efforts | Story Point
Sprint -1 ( 3-Weeks)[28/11/2024-18/12/2024]
1 | E1.2 | User Signup
|  | I. New User:- | Registration with (Mobile No, Email)
|  | II. New password | Password Creation ( support Password Policy)
|  | III. User Confirmation | ( OTP via mail /Mobile no)
2 | E2.1 | Expert Signup
|  | I. New Expert:- | Registration with (Mobile No, Email)
|  | II. New password | Password Creation ( support Password Policy)
|  | III. Expert Confirmation | ( OTP via mail /Mobile no)
Sprint -2 ( 3-Weeks) [19/12/2024- 8/01/2025]
3 | E1.1 | Web Page Creation | Web page will have different page link such as User Login, User Profile, Expert Login and Expert Profile, Product profile with description (what is it and purpose)
Sprint -3 ( 3-Weeks)[9/01/2025-29/01/2025]
4 |  | Testing
5 | E1.3 | User Profile Creation
|  | Name | Address, Mobile No/Alternate Mob no/Mail ID
6 | E2.2 | Expert Profile Creation
|  | Name | Address, Mobile No/Alternate Mob no/Mail ID
Sprint -4 ( 3-Weeks) [30/01/2025- 19/02/2025]
7 |  | Testing
8 | E1.4 | User Profile Management
|  | I. Existing Expert | Login ID/Expert ID, Password
|  | II. Forget Password | OTP activation
III. Security Questions
IV. Modification of Customer details
9 | E2.3 | Profile Management
|  | I. Existing User | Login ID/User ID, Password
|  | II. Forget Password | OTP activation
III. Security Questions
IV. Modification of Customer details
Sprint -5 ( 3-Weeks)[20/02/2025-12/03/2025]
10 |  | Testing
11 | E1.5 | User Search /Technical Query | Problem Statement, Expert Search, Connection, Resolution / Help Initiated
12 | E2.4 | Technical Query | Problem Statement, User Search, Connection, Resolution / Help Initiated
Sprint -6 ( 3-Weeks) [13/03/2025- 2/04/2025]
13 | E3.1 | Communicator
|  | I. Two-way Communication | Chat Communication, Voice Communication, Video Communication
|  | II. Screen Sharing for Problem Solving | 2 way screen sharing feature, Control sharing
|  | III. Secure Communication | Security with data saving and connectivity
Sprint -7 ( 3-Weeks)[3/04/2025-23/04/2025]
14 |  | Testing
15 | E1.6 | Payment mechanism to Trinade
16 | E2.5 | Payment mechanism to Expert from Trinade
Sprint -8 ( 3-Weeks)[24/04/2025-14/05/2025]
17 |  | Testing
18 | E3.2 | Rating & Review
|  | I. Rating Facility by User | Rating on the basis of Resolution time and Solution provided, Mainly by Users, Once committed cannot be changed
|  | II. Review comments by User | Review comments on the basis of Resolution time and Solution provided, Mainly by Users, Once submitted cannot be be modified.
|  | III. Visibility to eavery one included Experts. | Acknowledgement by Expert.
Sprint -9 ( 3-Weeks)[15/05/2025-4/06/2025]
19 | E3.3 | Database Management at Trinade End
|  | I. Storing all details | User profiles, Expert Profiles
|  | II. Maintaining History of Payments | Payment made by Users, Payment made to Experts, Commissions etc
|  | III. Maintain History of Resultion of problem | Queries & Resolutions history for particular duration at concent of Experts, Ratings and Comments
GA ( 1-Weeks) [5/05/2025- 25/06/2025]
20 |  | Testing | Complete Testing and Creating other documents
| NOTE:- | Epic-1 (E1) | POC for Video Recording and Processing
|  | Epic-2 (E2) | Image Processing
|  | Epic-3 (E3) | Face Recognition and Yawn Movement Recording
|  | Epic-4 (E4) | Illumination Setting with Camera

## Story
Epic No | Story No | Summary | Description | Story Point | Created By | Owned By | Start Date | Target Date | Time Spent | Status
Sprint-1 Creation of Sign up Page for User and Expert
E1 | 1 | As an administrator, I want to provide a link at home page for new Users to create an account. | Task 1. Create a link at home page. Task2. Navigation to Signup page | 2 | Ramnarayan | Akash
E1 | 2 | As an administrator, I want to create a page for Users so that new user can create an account. | Task 1. Creation of Signup page Task2. Creation of Password field via OTP. Task3. Creation to provide security Question. | 5 | Ramnarayan | Akash
E2 | 3 | As an administrator, I want to provide a link at home page for new Technical epert to create an account. | Task 1. Create a link at home page. Task2. Navigation to Signup page | 2 | Ramnarayan | Akash
E2 | 4 | As an administrator, I want to create a page for Technical expert so that new expert can create an account. | Task 1. Creation of Signup page Task2. Creation of Password field via OTP. Task3. Creation to provide security Question. | 5 | Ramnarayan | Akash
Sprint-2 Creation of Web Page/Home page for Different Linking
E1 | 1 | As an administrator, I want to create a Web Page like home page so that it can have detailed profile of Users and Experts, Product Profile (About), Payment and Review. | Task 1. Create a home page with all details. Task2. Create different sections such as Profiles, Payment, Review& Ratings etc. | 8 | Ramnarayan | Akash
E1 | 2 | As an administrator, I want to links for different section designed so that it can take to that particular page with details. | Task 1. Create links for different section at home page. Task2. Links to be particular for each section.. | 3 | Ramnarayan | Akash
Sprint-3 Creation of Profiles for User and Expert
E1 | 1 | As an administrator, I want to create a User profile to add all required details.(Name, Address, Mobile no). | Task 1. Creation of Profile with all details. | 5 | Ramnarayan | Akash
E2 | 2 | As an administrator, I want to create an Expert profile to add all required details.(Name, Address, Mobile no). | Task 1. Creation of Profile with all details. | 5 | Ramnarayan | Akash
Sprint-4 Development of Profile Management page for User and Expert
E1 | 1 | As an administrator, I want to Create a tab containing profile management which will have details for existing user, re-setting password with OTP, security questions etc. | Task 1. Provision of Editting option for Profile details. Task2. Provision for forget password and resetting it via OTP. | 5 | Ramnarayan | Akash
E2 | 2 | As an administrator, I want to Create a tab containing profile management which will have details for existing expert, re-setting password with OTP, security questions etc. | Task 1. Provision of Editting option for Profile details. Task2. Provision for forget password and resetting it via OTP. | 5 | Ramnarayan | Akash
Sprint-5 Development of Features for User Search and Technical Query
| 1 | As an administrator, I want design a page where User can be able to find out correct technical expert with his/her rating and charges. | Task1. User can see the list of expert on the basis of Problem staement. Task2. User can see the ratings and charges of all experts for his/her query. | 2 | Ramnarayan | Akash
| 2 | As an administrator, I want to design a page where user can put his/her technical query( problem statement) depending upon his expertise. | Task1. User can put his/her Problem staement as per selecting particular expert. | 2 | Ramnarayan | Akash
| 3 | As an administrator, I want to design a page where user can connect to Expert after putting his/her problem stamenet and start communication and then help can be initiated. | Task1. User can connect to the particular expert when s/he has selected as per his/her query. Task2. User can initiate communication anytime and get help. | 2 | Ramnarayan | Akash
| 4 | As an administrator, I want design a page where Expert can be able to check problem statement is any user put for resolution. | Task1. Expert can see any query falls in his/her bucket. | 2 | Ramnarayan | Akash
| 5 | As an administrator, I want to design a page where expert can connect to user after putting problem stamenet and help can be initiated by his/her side. | Task1. Expert can connect to user once user has ask for help. Task2. Expert can initiate communication anytime and provide help. | 2 | Ramnarayan | Akash
Sprint-6 Development of Communicator
E1 | 1 | As an administrator, I want to create a communicator so that we can support Text messaging or Chat communication between Users and Experts. | Task 1. Chat Communication established between Expert and user. Task2. Communication should be 2 ways communication. Task3. Communication to be secure. | 2 | Ramnarayan | Akash
E1 | 2 | As an administrator, I want to create a communicator so that we can support Voice calling between users and experts. | Task 1. Chat Communication established between Expert and user. Task2. Communication should be 2 ways communication. Task3. Communication to be secure. | 2 | Ramnarayan | Akash
| 3 | As an administrator, I want to create a communicator so that we can support Video Calling between users and experts. | Task 1. Chat Communication established between Expert and user. Task2. Communication should be 2 ways communication. Task3. Communication to be secure. | 5 | Ramnarayan | Akash
| 4 | As an administrator, I want to create a communicator so that we can support Screen Sharing\Desktop sharing during communication. | Task 1. Screen Sharing should be between Expert and user. Task2. Screen sharing must be secured and having control. | 5 | Ramnarayan | Akash
| 5 | As an administrator, I want to integrate all features of communicator so that fully secured communication can be done. | Task 1. Module to be integrated and ready for testing. | 5 | Ramnarayan | Akash
Sprint-7 Development of Payment Module
E1 | 1 | As an administrator, I want to create a RazorPay account so that it can be linked with Current account of Trinade | Task 1. Creation of RazorPay account and linking with Trinade current account. Task2. Test two way transaction using RazorPay account. | 5 | Ramnarayan | Akash
E1 | 2 | As an administrator, I want to Integrate RazorPay App to our Module so that transaction can be performed. | Task 1. Integration of RazorPay to Module. Task2. Support Refund process. Task3. Creation to provide security Question. | 5 | Ramnarayan | Akash
Sprint-8 Development of Rating and Review Features
E1 | 1 | As an administrator, I want to create a Rating windows so that users can rate expert. | Task 1. Creation of Rating windows Task2. Support for rating in terms of "*" | 5 | Ramnarayan | Akash
E1 | 2 | As an administrator, I want to create a Review comment windows so that users can provide review comments about expert. | Task 1. Creation of Review comment windows. Task2. Support for word counts | 3 | Ramnarayan | Akash
| 3 | As an administrator, I want to create a mechanism to sort all experts on the basis of rating and review comments so that top ranker can be obtained. | Task 1. Provision of sorting facility Task 2. Selction for expert with top ranking. | 3 | Ramnarayan | Akash
Sprint-9 Database and Security Management at Trinade
| 1 | As an administrator, I want to create a Databases so that we can store all details of users and Experts such as User profiles, Expert Profiles. | Task 1. Creation of Database to store contents of Users. Task2. Creation of Database to store contents of experts. | 3 | Ramnarayan | Akash
| 2 | As an administrator, I want to create a Databases so that we can store Maintaining History of Payments. | Task 1. Creation of Database to storethe history of Payment made by Users, Payment made to Experts, Commissions etc | 3 | Ramnarayan | Akash
| 3 | As an administrator, I want to create a Databases so that we can store Maintain History of Resultion of problem. | Task 1. Creation of Database to store Queries & Resolutions history for particular duration at concent of Experts, Ratings and Comments. | 3 | Ramnarayan | Akash

## Tasks_StoryWise
Sprint1
| Story 1 | As an administrator, I want to provide a link at home page for new Users to create an account. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Create a link at home page.
| 2 | Navigation to Signup page for User.
| Story 2 | As an administrator, I want to create a page for Users so that new user can create an account. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Create a Signup page
| 2 | Create a Password field via OTP.
| 3 | Create field to provide security Question and answer.
| Story 3 | As an administrator, I want to provide a link at home page for new Technical epert to create an account. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Create a link at home page.
| 2 | Navigation to Signup page for User.
| Story 4 | As an administrator, I want to create a page for Technical expert so that new expert can create an account. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Create a Signup page
| 2 | Create a Password field via OTP.
| 3 | Create field to provide security Question and answer.
Sprint2
| Story 1 | As an administrator, I want to create a Web Page like home page so that it can have detailed profile of Users and Experts, Product Profile (About), Payment and Review. | 8
| Task | Descriptions | Check Points | Efforts
| 1 | Create a home page with all details.
| 2 | Create different sections such as Profiles, Payment, Review& Ratings etc.
| Story 2 | As an administrator, I want to links for different section designed so that it can take to that particular page with details. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Create links for different section at home page.
| 2 | Create drilled links to be particular for each section..
Sprint3
| Story 1 | As an administrator, I want to create a User profile to add all required details.(Name, Address, Mobile no). | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Create Profile section with all details and add relevent data.
| Story 2 | As an administrator, I want to create an Expert profile to add all required details.(Name, Address, Mobile no). | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Create Profile section with all details and add relevent data.
Sprint4
| Story 1 | As an administrator, I want to Create a tab containing profile management which will have details for existing user, re-setting password with OTP, security questions etc. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Provide Editting option for Profile details of each section.
| 2 | Provide option for forget password and resetting it via OTP.
| Story 2 | As an administrator, I want to Create a tab containing profile management which will have details for existing expert, re-setting password with OTP, security questions etc. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Provide Editting option for Profile details of each section.
| 2 | Provide option for forget password and resetting it via OTP.
Sprint5
| Story 1 | As an administrator, I want design a page where User can be able to find out correct technical expert with his/her rating and charges. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | User can see the list of expert on the basis of Problem staement.
| 2 | User can see the ratings and charges of all experts for his/her query.
| Story 2 | As an administrator, I want to design a page where user can put his/her technical query( problem statement) depending upon his expertise. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | User can put his/her Problem staement as per selecting particular expert.
| Story 3 | As an administrator, I want to design a page where user can connect to Expert after putting his/her problem stamenet and start communication and then help can be initiated. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | User can connect to the particular expert when s/he has selected as per his/her query.
| 2 | User can initiate communication anytime and get help.
| Story 4 | As an administrator, I want design a page where Expert can be able to check problem statement is any user put for resolution. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Expert can see any query falls in his/her bucket.
| Story 5 | As an administrator, I want to design a page where expert can connect to user after putting problem stamenet and help can be initiated by his/her side. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Expert can connect to user once user has ask for help.
| 2 | Expert can initiate communication anytime and provide help.
Sprint6
| Story 1 | As an administrator, I want to create a communicator so that we can support Text messaging or Chat communication between Users and Experts. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Chat Communication established between Expert and user.
| 2 | Communication should be 2 ways communication.
| 3 | Communication to be secure.
| Story2 | As an administrator, I want to create a communicator so that we can support Voice calling between users and experts. | 2
| Task | Descriptions | Check Points | Efforts
| 1 | Voice Communication established between Expert and user.
| 2 | Communication should be 2 ways communication.
| 3 | Communication to be secure.
| Story 3 | As an administrator, I want to create a communicator so that we can support Video Calling between users and experts. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Video Communication established between Expert and user.
| 2 | Communication should be 2 ways communication.
| 3 | Communication to be secure.
| Story 4 | As an administrator, I want to create a communicator so that we can support Screen Sharing\Desktop sharing during communication. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Screen Sharing should be between Expert and user.
| 2 | Screen sharing must be secured and having control.
| Story 5 | As an administrator, I want to integrate all features of communicator so that fully secured communication can be done. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Module to be integrated and ready for testing.
Sprint7
| Story 1 | As an administrator, I want to create a RazorPay account so that it can be linked with Current account of Trinade. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of RazorPay account and linking with Trinade current account.
| 2 | Test two way transaction using RazorPay account.
| Story 2 | As an administrator, I want to Integrate RazorPay App to our Module so that transaction can be performed. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Integration of RazorPay to Module.
| 2 | Support Refund process.
| 3 | Creation to provide security Question.
Sprint8
| Story 1 | As an administrator, I want to create a Rating windows so that users can rate expert. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of Rating windows
| 2 | Support for rating in terms of "*"
| Story 2 | As an administrator, I want to create a Review comment windows so that users can provide review comments about expert. | 3
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of Review comment windows.
| 2 | Support for word counts
| Story 3 | As an administrator, I want to create a mechanism to sort all experts on the basis of rating and review comments so that top ranker can be obtained. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Provision of sorting facility
| 2 | Selction for expert with top ranking.
Sprint9
| Story 1 | As an administrator, I want to create a Databases so that we can store all details of users and Experts such as User profiles, Expert Profiles. | 3
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of Database to store contents of Users.
| 2 | Creation of Database to store contents of experts.
| Story 2 | As an administrator, I want to create a Databases so that we can store Maintaining History of Payments. | 3
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of Database to storethe history of Payment made by Users, Payment made to Experts, Commissions etc
| Story 3 | As an administrator, I want to create a Databases so that we can store Maintain History of Resultion of problem. | 5
| Task | Descriptions | Check Points | Efforts
| 1 | Creation of Database to store Queries & Resolutions history for particular duration at concent of Experts, Ratings and Comments.

## Risk Analysis
Development Risk:- |  |  | New potential risk
| 1 | Communicator (voice and Camera) | Hardware availability
| 2 | Linking this project details to our Main TRINADE Portal | Hardware software Integration
Installation on desk
Hardware Risk:-
Nil
Ubuntu OS installation
Technical Risk:-
| 1 | Payment permission from Razor Pay
| 2 | Software learning as n when required
Testing Risk:-
1

## Hardware
Trinade Requirement
1. System with RAM 32 GB /16 GB, HDD-1TB
2. Server for Application and Data Storage